## Portfolio Summary
GoKardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP
GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP | GoCardinal B2B Self-Service Travel Booking MVP
Project period: Aug 2022–May 2023 ¦ Role: Project Manager & Product Manager | Project period: Aug 2022–May 2023 ¦ Role: Project Manager & Product Manager ¦ Illustrative portfolio metrics are clearly labeled | Project period: Aug 2022–May 2023 ¦ Role: Project Manager & Product Manager ¦ Illustrative portfolio metrics are clearly labeled | Project period: Aug 2022–May 2023 ¦ Role: Project Manager & Product Manager ¦ Illustrative portfolio metrics are clearly labeled | Project period: Aug 2022–May 2023 ¦ Role: Project Manager & Product Manager ¦ Illustrative portfolio metrics are clearly labeled | Project period: Aug 2022–May 2023 ¦ Role: Project Manager & Product Manager ¦ Illustrative portfolio metrics are clearly labeled | Project period: Aug 2022–May 2023 ¦ Role: Project Manager & Product Manager ¦ Illustrative portfolio metrics are clearly labeled | Project period: Aug 2022–May 2023 ¦ Role: Project Manager & Product Manager ¦ Illustrative portfolio metrics are clearly labeled
Business context | GoCardinal served corporate travel clients through a manual request-and-response booking process. |  | PROJECT OBJECTIVES | PROJECT OBJECTIVES | PROJECT OBJECTIVES | PROJECT OBJECTIVES | PROJECT OBJECTIVES
Problem | Fares and itineraries could change while requests moved between customers and travel agents, increasing rework and slowing confirmation. |  | 1. Validate that the delay and fare-change problem was worth solving
Goal | Launch an MVP that allowed authorized corporate travelers to search and book itineraries while monitoring credit limits and travel spend. |  | 2. Reduce dependence on agent-mediated booking for routine trips
Responsibilities | User and market research, personas, use cases, requirements, backlog, wireframes, prototype, delivery planning, risk management, UAT and launch. |  | 3. Give customers visibility into credit limits and travel spend
MVP scope | Secure login; flight search; self-service booking; approval workflow; credit-limit visibility; itinerary status; spend dashboard. |  | 4. Protect corporate policies through approval and authorization controls
Delivery model | Hybrid Agile: discovery and stage gates followed by two-week development sprints, UAT, pilot and phased launch. |  | 5. Launch a measurable MVP within the Aug 2022–May 2023 window
Launch | Phased production launch in May 2023 with pilot customers, onboarding, training and hypercare.
Illustrative outcome | 75% activation, 60% 90-day adoption, 68% self-service booking share and 82% shorter booking turnaround.

## Project Timeline
MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule
MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule | MVP Project Timeline & Delivery Schedule
Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization. | Blue bars show the planned execution window. Dates and status can be edited for portfolio customization.
Workstream | Activity | Start | Finish | Owner | Deliverable | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Status
Initiation | Project charter and stakeholder alignment | 2022-08-01 | 2022-08-19 | PM/Product Manager | Approved charter | 1 | [9 empty] | Complete
Discovery | User interviews and workflow analysis | 2022-08-15 | 2022-09-16 | Product Manager | Research synthesis | 1 | 1 | [8 empty] | Complete
Discovery | Market and competitor research | 2022-08-22 | 2022-09-23 | Product Manager | Market-gap analysis | 1 | 1 | [8 empty] | Complete
Definition | Personas, journeys and use cases | 2022-09-12 | 2022-10-14 | Product Manager | Personas and use cases |  | 1 | 1 | [7 empty] | Complete
Definition | MVP requirements and prioritized backlog | 2022-10-03 | 2022-10-31 | PM/Product Manager | MVP scope baseline |  |  | 1 | [7 empty] | Complete
Design | Wireframes and clickable prototype | 2022-10-17 | 2022-11-25 | UX/Product | Validated prototype |  |  | 1 | 1 | [6 empty] | Complete
Planning | Architecture, integrations and release plan | 2022-11-14 | 2022-12-16 | Tech Lead/PM | Technical plan |  |  |  | 1 | 1 | [5 empty] | Complete
Build | Sprint 1: access, profile and flight search | 2023-01-02 | 2023-01-31 | Engineering | Search flow | [5 empty] | 1 |  |  |  |  | Complete
Build | Sprint 2: booking and approval workflow | 2023-02-01 | 2023-02-28 | Engineering | Booking flow | [6 empty] | 1 |  |  |  | Complete
Build | Sprint 3: credit and spend visibility | 2023-02-20 | 2023-03-17 | Engineering | Financial controls | [6 empty] | 1 | 1 |  |  | Complete
Test | System test, security review and UAT | 2023-03-06 | 2023-04-07 | QA/Business | UAT sign-off | [7 empty] | 1 | 1 |  | Complete
Launch | Pilot, training and change management | 2023-04-03 | 2023-05-05 | PM/Customer Success | Pilot readiness | [8 empty] | 1 | 1 | Complete
Launch | Production rollout and hypercare | 2023-05-08 | 2023-05-31 | PM/Engineering | MVP live | [9 empty] | 1 | Complete
[6 empty] | 44774 | 44805 | 44835 | 44866 | 44896 | 44927 | 44958 | 44986 | 45017 | 45047
[6 empty] | 44804 | 44834 | 44865 | 44895 | 44926 | 44957 | 44985 | 45016 | 45046 | 45077

## Product Backlog
MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog
MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog | MVP Product Backlog
MoSCoW prioritization; first seven items define the MVP release. | MoSCoW prioritization; first seven items define the MVP release. | MoSCoW prioritization; first seven items define the MVP release. | MoSCoW prioritization; first seven items define the MVP release. | MoSCoW prioritization; first seven items define the MVP release. | MoSCoW prioritization; first seven items define the MVP release. | MoSCoW prioritization; first seven items define the MVP release. | MoSCoW prioritization; first seven items define the MVP release. | MoSCoW prioritization; first seven items define the MVP release. | MoSCoW prioritization; first seven items define the MVP release.
ID | Epic | User story / capability | Priority | Story points | Release | Status | Acceptance criterion | Owner | Dependency
GC-01 | Access | Corporate user can securely sign in and manage a profile | Must | 8 | MVP | Done | Authorized users access only assigned company account | Engineering | Identity service
GC-02 | Search | Traveler can search live flight availability and fares | Must | 13 | MVP | Results show route, time, fare and availability | Engineering | Flight-content API | NIL
GC-03 | Booking | Traveler can select and confirm an itinerary | Must | 13 | MVP | Confirmed booking generates reference and itinerary | Engineering | Search + payment | NIL
GC-04 | Approvals | Booking routes to an approver when policy requires | Must | 8 | MVP | Approval status and audit trail are visible | Engineering | Company policy | NIL
GC-05 | Credit | Authorized user can view available corporate credit | Must | 8 | MVP | Displayed balance matches approved finance record | Engineering/Finance | Finance integration | NIL
GC-06 | Spend | Company admin can view current travel spend | Should | 5 | MVP | Dashboard totals reconcile to confirmed bookings | Data/Finance | Booking data | NIL
GC-07 | Itinerary | Traveler can view booking and itinerary status | Must | 5 | MVP | Latest confirmed itinerary is accessible | Engineering | Booking engine | NIL
GC-08 | Notifications | Users receive booking and approval notifications | Should | 5 | MVP | Event triggers email/SMS notification | Engineering | Messaging service | NIL
GC-09 | Reporting | Admin can export spend by traveler and period | Could | 5 | Phase 2 | Planned | CSV export matches dashboard filters | Data | Analytics
GC-10 | Policy | Admin can configure detailed travel policy rules | Should | 13 | Phase 2 | Planned | Rules block or route exceptions | Engineering | Admin module
GC-11 | Changes | Traveler can request changes or cancellation online | Could | 13 | Phase 2 | Planned | Request creates traceable service case | Engineering | Airline rules
GC-12 | Mobile | Responsive mobile-first booking experience | Could | 8 | Phase 2 | Planned | Core flows work on standard mobile viewport | UX/Engineering | Design system

## RAID Log
RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies
RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies | RAID Log — Risks, Assumptions, Issues & Dependencies
Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green. | Risk score = Probability × Impact. Scores 15–25 are red; 8–14 amber; 1–7 green.
ID | Type | Description | Probability (1–5) | Impact (1–5) | Score | Rating | Mitigation / response | Owner | Trigger | Status | Review date
R-01 | Risk | Flight-content API latency or outage affects search | 4 | 5 | 20 | High | Cache safe results; monitor API; agree escalation SLA | Tech Lead | Latency exceeds threshold | Open | 2023-01-15
R-02 | Risk | Fare changes between search and ticket confirmation | 4 | 4 | 16 | High | Display expiry; revalidate price before confirmation | Product Manager | Fare mismatch event | Mitigated | 2023-02-01
R-03 | Risk | Credit balance does not reconcile with finance records | 3 | 5 | 15 | High | Single source of truth; daily reconciliation; exception queue | Finance Lead | Variance detected | Open | 2023-02-15
R-04 | Risk | Customers continue sending manual booking requests | 4 | 4 | 16 | High | Pilot champions, onboarding, training and adoption dashboard | Customer Success | Self-service share below 40% | Open | 2023-04-15
R-05 | Risk | MVP scope expands beyond launch window | 4 | 3 | 12 | Medium | MoSCoW scope; change control; Phase 2 parking lot | Project Manager | New must-have request | Mitigated | 2022-11-30
R-06 | Risk | Personal or payment data exposure | 2 | 5 | 10 | Medium | Role-based access, encryption, security test and audit logs | Security Lead | Critical finding | Open | 2023-03-10
A-01 | Assumption | Pilot customers will provide UAT participants | 3 | 3 | 9 | Medium | Secure named testers and backup participants early | Project Manager | Tester gap | Validated | 2023-03-01
D-01 | Dependency | Engineering delivery depends on approved API credentials | 3 | 4 | 12 | Medium | Track credential request as launch-critical dependency | Tech Lead | Credential delay | Closed | 2022-12-15

## RACI
Delivery RACI | Delivery RACI | Delivery RACI | Delivery RACI | Delivery RACI | Delivery RACI | Delivery RACI
Delivery RACI | Delivery RACI | Delivery RACI | Delivery RACI | Delivery RACI | Delivery RACI | Delivery RACI
Activity | PM / Product Manager | Executive Sponsor | Engineering Lead | UX / Research | Finance / Ops | Customer Success
Charter and business case | R/A | A | C | C | C | I
User and market research | R/A | I | C | R | C | C
Personas and use cases | R/A | I | C | R | C | C
MVP scope and backlog | R/A | C | C | C | C | C
Technical architecture | C | I | R/A | C | C | I
Wireframes and prototype | A | I | C | R | C | C
Sprint delivery | A | I | R | C | C | I
UAT and launch readiness | R/A | I | R | C | C | R
Customer onboarding | A | I | C | I | C | R
Adoption measurement | R/A | I | C | C | C | R

## Adoption Dashboard
MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics
MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics | MVP Launch & Adoption Dashboard — Illustrative Metrics
90-day portfolio model following the May 2023 phased launch. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results. | 90-day portfolio model following the May 2023 phased launch. Values are illustrative, not verified GoCardinal results.
Activation rate | Activation rate | Activation rate | 90-day adoption | 90-day adoption | 90-day adoption | Self-service share | Self-service share | Self-service share | Turnaround reduction | Turnaround reduction | Turnaround reduction
75% |  |  | 60% |  |  | 68% |  |  | 82.22%
Month | Activated users | MAU | Self-service share
May-23 | 100 | 80 | 40%
Jun-23 | 180 | 145 | 60%
Jul-23 | 225 | 180 | 68%
Operational KPI | Baseline | Month 3 | Change
Average booking turnaround (min) | 45 | 8 | -82.22%
Requote/error rate | 18% | 6% | -66.67%
Self-service bookings / month | 0 | 612 | 612
Estimated staff capacity released (hours) | 0 | 377.4 | 377.4

## Adoption Data
Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data
Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data | Illustrative 90-Day Adoption Data
Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance. | Synthetic portfolio data; replace with verified analytics before presenting as actual company performance.
Month | Eligible users | Invited users | Activated users | Monthly active users | Total bookings | Self-service bookings | Activation rate | Adoption rate | Self-service share | Avg booking time (min) | Requote/error rate
May-23 | 300 | 180 | 100 | 80 | 400 | 160 | 55.56% | 26.67% | 40% | 20 | 12%
Jun-23 | 300 | 260 | 180 | 145 | 650 | 390 | 69.23% | 48.33% | 60% | 12 | 8%
Jul-23 | 300 | 300 | 225 | 180 | 900 | 612 | 75% | 60% | 68% | 8 | 6%