## Slide 1
PRODUCT + PROJECT MANAGEMENT PORTFOLIO
Turning corporate travel requests into self-service booking
Gokardinal B2B SaaS MVP
August 2022–May 2023
45 min
manual booking turnaround
8 min
self-service turnaround
Month 3
Agnes Iwaye | Project Manager & Product Manager

## Slide 2
Manual request cycles created avoidable fare and itinerary risk
02
BEFORE
Agent-mediated booking
Customer sends request → agent searches → options are returned → customer responds → agent rechecks availability.
Business impact
Slower confirmation • more requotes • limited spend visibility • higher service workload
OPPORTUNITY
Corporate self-service
Give authorized customers live search, controlled booking, approval routing, credit visibility and spend reporting in one platform.
Product principle
Increase customer control without removing corporate policy and financial governance.

## Slide 3
Discovery tested the problem before the team committed to an MVP
03
USER RESEARCH
Mapped the request-to-ticket workflow, delay points, approval needs, credit questions and user confidence.
MARKET RESEARCH
Compared corporate booking experiences, self-service capabilities, policy controls and reporting gaps.
PRODUCT DEFINITION
Converted evidence into personas, journeys, use cases, requirements, success measures and a prioritized backlog.
Primary personas
Corporate traveler
Fast, accurate itinerary booking
Travel approver
Policy-compliant decisions and audit trail
Company administrator
Credit, spend and traveler visibility

## Slide 4
The MVP balanced customer autonomy with corporate control
04
MUST HAVE
Secure login
Live flight search
Self-service booking
Approval workflow
Credit-limit visibility
Itinerary status
SHOULD HAVE
Spend dashboard
Booking notifications
Basic company administration
Operational audit trail
PHASE 2
Policy-rule configuration
Online changes/cancellations
Advanced reporting
Mobile optimization
Expanded integrations
Scope rule: any new request had to protect launch value, fit the May 2023 window, or move to the Phase 2 backlog.

## Slide 5
The redesigned journey removed handoffs from routine bookings
05
MANUAL JOURNEY
SELF-SERVICE MVP
Send request
Sign in
Agent searches
Search live fares
Review options
Approve if needed
Recheck + confirm
Book + track spend
Multiple response delays and fare revalidation
Live information, policy control and immediate confirmation

## Slide 6
A ten-month roadmap moved from evidence to phased launch
06
AUG
SEP
OCT
NOV
DEC
JAN
FEB
MAR
APR
MAY
Initiate + discover
Define MVP
Design + validate
Build sprints
Test + UAT
Pilot + launch
2022
2023

## Slide 7
Hybrid governance kept discovery, delivery and launch decisions visible
07
Decision / activity | PM + Product | Sponsor | Engineering | UX / Research | Finance / Ops | Customer Success
Business case and charter | R/A | A | C | C | C | I
User research and personas | R/A | I | C | R | C | C
MVP backlog and scope | R/A | C | C | C | C | C
Architecture and integrations | C | I | R/A | C | C | I
UAT and launch readiness | R/A | I | R | C | C | R
Onboarding and adoption | A | I | C | I | C | R
Operating rhythm: two-week sprints • weekly risk review • backlog refinement • stage-gate UAT and launch approval

## Slide 8
Launch risks were managed through product and delivery controls
08
Risk | Rating | Primary response
Flight-content API outage | High | Cache safe results; monitoring; escalation SLA
Fare changes before confirmation | High | Revalidate price and availability at confirmation
Credit data mismatch | High | Single source; daily reconciliation; exception queue
Low customer adoption | High | Pilot champions, onboarding and adoption tracking
Scope expansion | Medium | MoSCoW, change control and Phase 2 backlog
Data/security exposure | High | Role-based access, encryption, testing and audit logs
Risk response priorities
Protect live price accuracy
Protect corporate financial data
Protect customer trust at launch
Protect the May 2023 scope boundary

## Slide 9
The launch sequence reduced risk before full customer exposure
09
1 PILOT
Select representative companies
Confirm workflows and permissions
Capture critical defects
2 ENABLE
Train users and approvers
Publish guides and support paths
Confirm data readiness
3 LAUNCH
Phased production access
Daily adoption monitoring
Executive status updates
4 HYPERCARE
Prioritize launch issues
Measure self-service behavior
Move enhancements to backlog
Go / no-go criteria
No critical security defects • core booking flow passed • credit data reconciled • support team ready • pilot acceptance received

## Slide 10
Illustrative 90-day metrics show how MVP success would be measured
10
75%
activation rate
60%
eligible-user adoption
68%
self-service booking share
82%
shorter booking turnaround
Chart: 
| Launch | Month 2 | Month 3
Activated users | 100 | 180 | 225
Monthly active users | 80 | 145 | 180
Operational effect
45 → 8 min
booking turnaround
18% → 6%
requote/error rate